## Dashboard
Ticket # | Status | Street | Cross Street | Done For | Work Type | Depth | Expires | Total Resp | Marked | Clear | Unmarked | Exceptions | No Response | Unmarked Companies | Notes/Remarks
26021005726 | AWAITING LOCATE | CLINT CIR | LINCOLN AVE | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 5 | 1 | 2 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ AT&T - DISTRIBUTION: Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name
26021005778 | AWAITING LOCATE | CLINT CIR | LINCOLN AVE | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 7 | 5 | 0 | 2 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ AT&T - DISTRIBUTION: Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name
26021005797 | CLEAR TO DIG | HALSTON DR | LINCOLN AVE | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 7 | 1 | 0 | 0 | 0
26021005812 | AWAITING LOCATE | HALSTON CIR | HALSTON DR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 6 | 1 | 1 | 0 | 0 | CENTERPOINT ENERGY (SOUTH) (GAS) | CENTERPOINT ENERGY (SOUTH): Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified t
26021005817 | CLEAR TO DIG | HALSTON CIR | HALSTON DR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 7 | 1 | 0 | 0 | 0
26021005823 | AWAITING LOCATE | HALSTON CIR | HALSTON DR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 5 | 3 | 1 | 0 | 0 | CENTERPOINT ENERGY (SOUTH) (GAS) | CENTERPOINT ENERGY (SOUTH): Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified t
26021005864 | AWAITING LOCATE | PRESCOT DR | HALSTON CIR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 3 FT | 03/02/2026 | 8 | 5 | 1 | 2 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ AT&T - DISTRIBUTION: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate
26021005866 | AWAITING LOCATE | HALSTON CIR | HALSTON DR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 3 FT | 03/02/2026 | 8 | 5 | 2 | 1 | 0 | 0 | CENTERPOINT ENERGY (SOUTH) (GAS) | CENTERPOINT ENERGY (SOUTH): Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified t
26021005867 | AWAITING RESPONSE | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 3 FT | 03/02/2026 | 8 | 2 | 1 | 4 | 0 | 1 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); NEWBURGH, TOWN OF (SEWER); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH): Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified t ¦ NEWBU
26021005889 | AWAITING LOCATE | HUNTINGTON RIDGE CIR | LINCOLN AVE | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 4 | 1 | 3 | 0 | 0 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC) | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate
26021005894 | AWAITING LOCATE | HUNTINGTON RIDGE CIR | EMILY CT | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 4 | 1 | 3 | 0 | 0 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC) | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate
26021005901 | AWAITING LOCATE | MILLICENT CT | HUNTINGTON RIDGE CIR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 3 | 3 | 3 | 0 | 0 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC) | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate
26021005904 | AWAITING LOCATE | W EMILY CT | HUNTINGTON RIDGE CIR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 3 | 2 | 3 | 0 | 0 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC) | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate
26021005911 | AWAITING LOCATE | HUNTINGTON RIDGE CIR | EMILY CT | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 4 | 1 | 3 | 0 | 0 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC) | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST
26021005915 | AWAITING LOCATE | STONECREEK CIR | FRAME RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 2 | 2 | 5 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTE
26021005918 | AWAITING LOCATE | STONECREEK CIR | FRAME RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 2 | 1 | 5 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFEAL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTE
26021005922 | AWAITING LOCATE | FRAME RD | STONECREEK CIR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 2 | 1 | 6 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); MAINSTREAM FIBER NETWORKS, LLC (FIBER OPTIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTE
26021005933 | AWAITING LOCATE | BLACKSTONE DR | S FRAME RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 2 | 3 | 4 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTERPOINT ENERGY (SOUTH ELECTRIC): Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ AT&T - DISTRIBUTION: Date:02/
26021005942 | AWAITING LOCATE | WILLOWBEND DR | S FRAME RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 9 | 2 | 2 | 5 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTE
26021005946 | AWAITING LOCATE | WINDHILL LN | WILLOWBEND DR | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/02/2026 | 8 | 2 | 1 | 5 | 0 | 0 | INSIGHT COMMUNICATIONS (NEW ALBANY) (CABLE TV); RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND (CABLE TV, COMMUNICATIONS, FIBER OPTIC); CENTERPOINT ENERGY (SOUTH) (GAS); CENTERPOINT ENERGY (SOUTH ELECTRIC) (ELECTRIC); AT&T - DISTRIBUTION (COMMUNICATIONS) | INSIGHT COMMUNICATIONS (NEW ALBANY): Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622 ¦ RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND: Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 20 ¦ CENTERPOINT ENERGY (SOUTH): Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ¦ CENTE
26021601665 | EXCEPTIONS | SAILER RD | BLACKFORD RD E | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/08/2026 | 6 | 3 | 2 | 0 | 1 | 0 | CENTERPOINT ENERGY (SOUTH) (GAS) | CENTERPOINT ENERGY (SOUTH): Date:02/20/2026 07:55 AM Respondent:CAMERON RITCHIE CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021601984 | CLEAR TO DIG | SAILER RD | E BLACKFORD RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/08/2026 | 7 | 3 | 4 | 0 | 0 | 0
26021602061 | CLEAR TO DIG | E BLACKFORD RD | SAILER RD | MAINSTREAM | DIRECTIONAL DRILLING - CONDUIT | 4 FT | 03/08/2026 | 7 | 4 | 3 | 0 | 0 | 0

## Utility Responses
Ticket # | Street | Cross Street | Expires | Utility Company | Utility Type | Status | Response Detail
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Date:02/12/2026 12:02 PM IN AMERICAN WATER SEWER, WATER
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/13/2026 04:44 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Date:02/23/2026 10:53 AM Respondent:CENTERPOINT MDI ALL_GAS FACILITY LOCATED. MARKER POST AND BALL PLACED. VERIFIED MAIN. CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Date:02/17/2026 08:24 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-17 11:13:37 MAINSTREAM FIBER NETWORKS, LLC FIBER OPTIC
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/11/2026 06:30 AM NEWBURGH, TOWN OF SEWER
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/13/2026 11:46 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005726 | CLINT CIR | LINCOLN AVE | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Date:02/12/2026 12:02 PM IN AMERICAN WATER SEWER, WATER
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/13/2026 04:44 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Date:02/17/2026 08:24 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-17 11:19:51 CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Date:02/17/2026 08:24 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-17 11:19:51 NEWBURGH, TOWN OF SEWER
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/13/2026 11:46 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005778 | CLINT CIR | LINCOLN AVE | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 03:51 PM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 09:12 AM
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:05 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-19 14:02:32
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:05 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-19 14:02:32
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005797 | HALSTON DR | LINCOLN AVE | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 03:45 PM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 01:20 PM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 09:12 AM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified to resolve the issue. Per Indiana Law, the operator shall notify the excavator responsible of their determination and shall provide additional information. Date:02/18/2026 07:45 AM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/18/2026 07:45 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: 9080 HALSTON CIRCLE, 9101 HALSTON CIRCLE 9105 HALSTON CIRCLE, GAS STUB COMING ACROSS BOTH ADDRESS FRONT YARDS ARE UNLOCATABLE, GAS STOP
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005812 | HALSTON CIR | HALSTON DR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 01:16 PM
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 08:48 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 09:12 AM
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:15 AM Respondent:CENTERPOINT MDI ALL_GAS LOCATED GAS MAIN ACROSS ROAD AT INTERSECTION. VAC RIG AND VERIFIED.
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 08:24 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: INTERSECTION OF PRESCOTT DR AND HALSTON, WE NEED THE GAS MAIN CROSSING THE INTERSECTION MARKED UP GOING FROM THE MAIN ON THE SOUTH SIDE
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 05:42 AM
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005817 | HALSTON CIR | HALSTON DR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 08:45 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 10:31 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 09:12 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified to resolve the issue. Per Indiana Law, the operator shall notify the excavator responsible of their determination and shall provide additional information. Date:02/18/2026 07:45 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/18/2026 07:45 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: 9080 HALSTON CIRCLE, 9101 HALSTON CIRCLE 9105 HALSTON CIRCLE, GAS STUB COMING ACROSS BOTH ADDRESS FRONT YARDS ARE UNLOCATABLE, GAS STOP
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 05:42 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005823 | HALSTON CIR | HALSTON DR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/17/2026 10:25 AM
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 09:12 AM
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:30 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-19 14:24:21
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:30 AM Respondent:OTS LOCATING DATECOMPLETED: 2026-02-19 14:24:21
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005864 | PRESCOT DR | HALSTON CIR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 02:26 PM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:44 AM
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 06:45 AM
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified to resolve the issue. Per Indiana Law, the operator shall notify the excavator responsible of their determination and shall provide additional information. Date:02/18/2026 07:45 AM
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/18/2026 07:45 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: 9080 HALSTON CIRCLE, 9101 HALSTON CIRCLE 9105 HALSTON CIRCLE, GAS STUB COMING ACROSS BOTH ADDRESS FRONT YARDS ARE UNLOCATABLE, GAS STOP
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 09:16 AM
26021005866 | HALSTON CIR | HALSTON DR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/16/2026 02:20 PM
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 06:57 AM
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Line is untonable - Do not excavate until resolved. The line is untonable and the utility has been notified to resolve the issue. Per Indiana Law, the operator shall notify the excavator responsible of their determination and shall provide additional information. Date:02/19/2026 11:50 AM
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/19/2026 11:50 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: LOCATE AND VERIFY 100 FT RADIUS OF CLINT CIRCLE. UNLOCATABE 2 INCH PLASTIC MAIN GOING ACROSS LINCOLN TAPPING INTO 4 INCH PLASTIC MAIN D
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | NO RESPONSE | [No Response Recorded]
26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 11:50 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/13/2026 04:44 AM
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 06:15 AM
26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 11:46 AM
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 10:12 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 06:57 AM
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/18/2026 06:04 AM
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | BP PIPELINES NORTH AMERICA, INC. | PIPELINE | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 04:33 AM Respondent:LEVI KISSINGER
26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 10:07 AM
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/13/2026 02:41 PM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 06:57 AM
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 06:30 AM
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 06:15 AM
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | BP PIPELINES NORTH AMERICA, INC. | PIPELINE | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 04:32 AM Respondent:LEVI KISSINGER
26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/13/2026 02:38 PM
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/16/2026 06:50 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/14/2026 06:57 AM
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Unmarked - Marking Delay - Do not excavate until resolved. Excavation site is unmarked; markings are delayed. The locate technician cannot mark within two full working days or by the requested start date and time, whichever is later. Per Indiana Law, the operator shall notify the excavator responsib
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Marked - Underground facilities in the proposed excavation area have been marked. Date:02/17/2026 06:15 AM
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | BP PIPELINES NORTH AMERICA, INC. | PIPELINE | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/11/2026 04:32 AM Respondent:LEVI KISSINGER
26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | CLEAR | Clear - No underground facilities are in the proposed excavation or design area. Date:02/16/2026 06:46 AM
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | MARKED | Date:02/16/2026 10:15 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) 2026/02/12 04:15 PROJECT WORKING WITH RAF TO GET AREAS MARKED DAILY FOR EACH CREW 2026/02/12 04:15 RESCHEDULE APPROVED BY: RAFFE 8901233456 2026/02/22 18:26 NO MESSAGE LEFT. LARGE MULTI SUBDIVISION PROJECT 2026/02/22 18:26 RESCHEDUL
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:13 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:13 IN AMERICAN WATER SEWER, WATER
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/14/2026 06:57 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:34 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:34 CENTERPOINT ENERG
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:34 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:34 NEWBURGH, TOWN OF
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/17/2026 06:15 AM BP PIPELINES NORTH AMERICA, INC. PIPELINE
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | BP PIPELINES NORTH AMERICA, INC. | PIPELINE | CLEAR | Date:02/11/2026 04:31 AM Respondent:LEVI KISSINGER AT&T - DISTRIBUTION COMMUNICATIONS
26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Date:02/16/2026 10:10 AM
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:28 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:28 IN AMERICAN WATER SEWER, WATER
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/16/2026 06:45 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:44 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:44 CENTERPOINT ENERG
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:44 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:44 MAINSTREAM FIBER
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/11/2026 06:30 AM CHANDLER UTILITIES SEWER, STORM, WATER
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Date:02/11/2026 05:42 AM NEWBURGH, TOWN OF SEWER
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/18/2026 06:04 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005915 | STONECREEK CIR | FRAME RD | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFEAL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:40 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:40 IN AMERICAN WATER SEWER, WATER
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/16/2026 06:57 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:52 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:52 CENTERPOINT ENERG
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:52 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:52 CHANDLER UTILITIE
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Date:02/11/2026 05:42 AM NEWBURGH, TOWN OF SEWER
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/18/2026 06:04 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005918 | STONECREEK CIR | FRAME RD | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:52 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:52 IN AMERICAN WATER SEWER, WATER
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/14/2026 09:47 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:01 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:01 CENTERPOINT ENERG
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:01 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:01 MAINSTREAM FIBER
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | UNMARKED | Date:02/12/2026 12:41 PM Attempted to contact: RAFAEL, Comments : DELAYED DUE TO TICKET VOLUME CHANDLER UTILITIES SEWER, STORM, WATER
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | MARKED | Date:02/11/2026 11:41 AM NEWBURGH, TOWN OF SEWER
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | CLEAR | Date:02/18/2026 06:05 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005922 | FRAME RD | STONECREEK CIR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | CLEAR | Date:02/11/2026 05:49 AM IN AMERICAN WATER SEWER, WATER
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/14/2026 09:47 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:09 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:09 CENTERPOINT ENERG
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:09 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:09 MAINSTREAM FIBER
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/11/2026 06:30 AM CHANDLER UTILITIES SEWER, STORM, WATER
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Date:02/11/2026 05:42 AM NEWBURGH, TOWN OF SEWER
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/23/2026 05:00 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005933 | BLACKSTONE DR | S FRAME RD | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:03 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:03 IN AMERICAN WATER SEWER, WATER
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/14/2026 09:47 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:19 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:19 CENTERPOINT ENERG
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:19 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:19 MAINSTREAM FIBER
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/11/2026 06:30 AM CHANDLER UTILITIES SEWER, STORM, WATER
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Date:02/11/2026 05:42 AM NEWBURGH, TOWN OF SEWER
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/23/2026 05:00 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005942 | WILLOWBEND DR | S FRAME RD | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | UNMARKED | Date:02/20/2026 07:59 AM Respondent:BENJAMIN GROSSMAN ( IN (USIC) ) Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 02/20/2026 at 09:54 AM, Comment
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | RCN TELECOM SERVICES OF ILLINOIS, LLC DBA ASTOUND BROADBAND | CABLE TV, COMMUNICATIONS, FIBER OPTIC | UNMARKED | Date:02/12/2026 08:53 AM Attempted to contact: RAFAEL RIVAS, Comments : RAFAEL - CHANGED FROM: 2026-02-13 06:00:00 TO 2026-03-02 06:00:18 - EXCAVATION DATE CHANGED FROM: 2026-02-13 07:00:00 TO: 2026-03-02 07:00:18 IN AMERICAN WATER SEWER, WATER
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | IN AMERICAN WATER | SEWER, WATER | MARKED | Date:02/14/2026 09:47 AM CENTERPOINT ENERGY (SOUTH) GAS
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | UNMARKED | Date:02/19/2026 01:02 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:27 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:27 CENTERPOINT ENERG
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | UNMARKED | Date:02/19/2026 01:03 PM Respondent:OTS LOCATING Attempted to contact: RAFAEL RIVAS, Comments : NATHAN. PRIORITIES LIST ALREADY GIVEN BY CONTRACTOR - CHANGED FROM: 2026-02-20 06:00:45 TO 2026-02-27 06:00:27 - EXCAVATION DATE CHANGED FROM: 2026-02-20 07:00:45 TO: 2026-02-27 07:00:27 CHANDLER UTILITIE
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | CHANDLER UTILITIES | SEWER, STORM, WATER | CLEAR | Date:02/11/2026 05:42 AM NEWBURGH, TOWN OF SEWER
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | NEWBURGH, TOWN OF | SEWER | MARKED | Date:02/23/2026 05:00 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021005946 | WINDHILL LN | WILLOWBEND DR | 03/02/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | UNMARKED | Date:02/20/2026 07:55 AM Attempted to contact: RAFAEL RIVAS via Phone 4702622280 on 02/20/2026 at 09:54 AM, Locator Name: BENJAMIN GROSSMAN, Locator phone/email: BENJAMINGROSSMAN@USICLLC.COM, Proposed Date/Time of Completion: 03/02/2026 at 09:54 AM, Comments : NO MESSAGE LEFT ONGOING PROJECT
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED WITH EXCEPTIONS | Date:02/20/2026 07:55 AM Respondent:CAMERON RITCHIE CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Date:02/18/2026 11:49 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: UNABLE TO LOCATE END OF MAIN IN FRONT OF ADDRESS 3925 SAILOR RD STOP STICK HAS BEEN PLACED. DATECOMPLETED: 2026-02-18 14:42:35 MAINSTREAM FIBER NETWORKS, LLC FIBER OPTIC
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/17/2026 08:54 AM GERMAN TOWNSHIP WATER DISTRICT WATER
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | GERMAN TOWNSHIP WATER DISTRICT | WATER | MARKED | Date:02/16/2026 09:27 AM COUNTRYMARK REFINING & LOGISTICS, LLC PIPELINE
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | COUNTRYMARK REFINING & LOGISTICS, LLC | PIPELINE | CLEAR | Date:02/16/2026 07:22 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021601665 | SAILER RD | BLACKFORD RD E | 03/08/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Date:02/18/2026 08:02 AM
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | CLEAR | Date:02/18/2026 08:13 AM Respondent:ANDREW PETTY ( IN (USIC) ) CENTERPOINT ENERGY (SOUTH) GAS
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Date:02/20/2026 07:34 AM Respondent:CENTERPOINT MDI ALL_GAS LOCATED. PAINT AND FLAGS DOWN CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Date:02/18/2026 11:55 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: UNABLE TO LOCATE END OF MAIN IN FRONT OF ADDRESS 3925 SAILOR RD STOP STICK HAS BEEN PLACED. ALSO UNABLE TO LOCATE THE 2IN STEEL GAS MAIN AT THE INTERTERSECTION OF SAILOR RD AND E BLACKFORD RD. STOP STICK HAS BEEN PLAC
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/17/2026 08:57 AM GERMAN TOWNSHIP WATER DISTRICT WATER
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | GERMAN TOWNSHIP WATER DISTRICT | WATER | MARKED | Date:02/16/2026 09:28 AM COUNTRYMARK REFINING & LOGISTICS, LLC PIPELINE
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | COUNTRYMARK REFINING & LOGISTICS, LLC | PIPELINE | CLEAR | Date:02/16/2026 08:07 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021601984 | SAILER RD | E BLACKFORD RD | 03/08/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | CLEAR | Date:02/18/2026 08:07 AM
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | INSIGHT COMMUNICATIONS (NEW ALBANY) | CABLE TV | CLEAR | Date:02/18/2026 08:10 AM Respondent:ANDREW PETTY ( IN (USIC) ) CENTERPOINT ENERGY (SOUTH) GAS
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | CENTERPOINT ENERGY (SOUTH) | GAS | MARKED | Date:02/20/2026 08:11 AM Respondent:CENTERPOINT MDI ALL_GAS LOCATED AND PAINTED CENTERPOINT ENERGY (SOUTH ELECTRIC) ELECTRIC
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | CENTERPOINT ENERGY (SOUTH ELECTRIC) | ELECTRIC | MARKED | Date:02/18/2026 11:33 AM Respondent:OTS LOCATING UNLOCATABLE VERIFIED EXPLANATION: UNABLE TO LOCATE GAS SERVICE FOR 4307 E BLACKFORD; SIGNAL DIES IN FRONT YARD BEFORE MAIN; UNLOCATABLE 2\&QUOT; STL GAS MAIN AT INTERSECTION OF E BLACKFORD AND SAILER. NO WORK ORDER TO INDICATE HOW MAINS INTERSECT; NEE
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | MAINSTREAM FIBER NETWORKS, LLC | FIBER OPTIC | CLEAR | Date:02/17/2026 08:58 AM GERMAN TOWNSHIP WATER DISTRICT WATER
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | GERMAN TOWNSHIP WATER DISTRICT | WATER | MARKED | Date:02/16/2026 09:28 AM COUNTRYMARK REFINING & LOGISTICS, LLC PIPELINE
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | COUNTRYMARK REFINING & LOGISTICS, LLC | PIPELINE | CLEAR | Date:02/16/2026 08:07 AM AT&T - DISTRIBUTION COMMUNICATIONS
26021602061 | E BLACKFORD RD | SAILER RD | 03/08/2026 | AT&T - DISTRIBUTION | COMMUNICATIONS | MARKED | Date:02/18/2026 08:04 AM

## Expirations
Expires | Ticket # | Street | Cross Street | Status | Unmarked Count | Done For
03/02/2026 | 26021005726 | CLINT CIR | LINCOLN AVE | AWAITING LOCATE | 2 | MAINSTREAM
03/02/2026 | 26021005778 | CLINT CIR | LINCOLN AVE | AWAITING LOCATE | 2 | MAINSTREAM
03/02/2026 | 26021005797 | HALSTON DR | LINCOLN AVE | CLEAR TO DIG | 0 | MAINSTREAM
03/02/2026 | 26021005812 | HALSTON CIR | HALSTON DR | AWAITING LOCATE | 1 | MAINSTREAM
03/02/2026 | 26021005817 | HALSTON CIR | HALSTON DR | CLEAR TO DIG | 0 | MAINSTREAM
03/02/2026 | 26021005823 | HALSTON CIR | HALSTON DR | AWAITING LOCATE | 1 | MAINSTREAM
03/02/2026 | 26021005864 | PRESCOT DR | HALSTON CIR | AWAITING LOCATE | 2 | MAINSTREAM
03/02/2026 | 26021005866 | HALSTON CIR | HALSTON DR | AWAITING LOCATE | 1 | MAINSTREAM
03/02/2026 | 26021005867 | OUTER LINCOLN AVE | HUNTINGTON RIDGE CIR | AWAITING RESPONSE | 4 | MAINSTREAM
03/02/2026 | 26021005889 | HUNTINGTON RIDGE CIR | LINCOLN AVE | AWAITING LOCATE | 3 | MAINSTREAM
03/02/2026 | 26021005894 | HUNTINGTON RIDGE CIR | EMILY CT | AWAITING LOCATE | 3 | MAINSTREAM
03/02/2026 | 26021005901 | MILLICENT CT | HUNTINGTON RIDGE CIR | AWAITING LOCATE | 3 | MAINSTREAM
03/02/2026 | 26021005904 | W EMILY CT | HUNTINGTON RIDGE CIR | AWAITING LOCATE | 3 | MAINSTREAM
03/02/2026 | 26021005911 | HUNTINGTON RIDGE CIR | EMILY CT | AWAITING LOCATE | 3 | MAINSTREAM
03/02/2026 | 26021005915 | STONECREEK CIR | FRAME RD | AWAITING LOCATE | 5 | MAINSTREAM
03/02/2026 | 26021005918 | STONECREEK CIR | FRAME RD | AWAITING LOCATE | 5 | MAINSTREAM
03/02/2026 | 26021005922 | FRAME RD | STONECREEK CIR | AWAITING LOCATE | 6 | MAINSTREAM
03/02/2026 | 26021005933 | BLACKSTONE DR | S FRAME RD | AWAITING LOCATE | 4 | MAINSTREAM
03/02/2026 | 26021005942 | WILLOWBEND DR | S FRAME RD | AWAITING LOCATE | 5 | MAINSTREAM
03/02/2026 | 26021005946 | WINDHILL LN | WILLOWBEND DR | AWAITING LOCATE | 5 | MAINSTREAM
03/08/2026 | 26021601665 | SAILER RD | BLACKFORD RD E | EXCEPTIONS | 0 | MAINSTREAM
03/08/2026 | 26021601984 | SAILER RD | E BLACKFORD RD | CLEAR TO DIG | 0 | MAINSTREAM
03/08/2026 | 26021602061 | E BLACKFORD RD | SAILER RD | CLEAR TO DIG | 0 | MAINSTREAM